2012 Meeting of the NTHMP Warning Coordination Sub. Action Items

February 7, 2012 – San Diego, CA

Update – January 27, 2013

| Action | Date | Resp. Person(s) | Status |
| --- | --- | --- | --- |
| 1: Send term Tsunami Height with short definition to WCS for final review. | 3/12 | WCS co-chairs | Done |
| 2: Tiger Team (Rizzo, Schelling, Miller, Richards, Bailey, Nicolini, Preller, Lorens) to recommend solution to Tsunami Advisory EAS activation. | 5/12 | Althea Rizzo (lead) | Done – Rizzo to report at meeting |
| 3: Determine state of CA position on changing EAS RMT test to March. Dependent on this response, WCS take actions to change date in 2014. | 3/12 | Kevin Miller – CA EMA. WCS co-chairs | CA in favor of moving to March |
| 4: Propose March 20, 2013 for Lantex13 at ICG meeting and provide response to co-chairs. | 4/12 | Christa von Hillebrandt | Done |
| 5: Send out proposed date of March 27, 2013 for Pacifex12 to WCS for input and/or approval. | 3/12 | WCS co-chairs | Done |
| 6: Create 2013 Lantex Manual. | 9/12 | WCATWC - PTWC | Complete and passed to CTWP for finalization |
| 7: Create 2013 Pacifex Manual. | 9/12 | WCATWC - PTWC | Complete and posted to WCATWC web site 1/1/13 |
| 8: ITIC to inform WCS co-chairs of plans for PacWave in 2013 as plans materialize. | 7/12 | ITIC | August, 2013 |
| 9: Update post-event survey based on input from last year’s process using Survey Monkey if possible. | 3/12 | WCS co-Chairs | Done |
| 10: Update post-event survey implementation plan based on lessons learned from this year and provide to CC for approval. | 4/12 | WCS co-Chairs | Not Done – Survey is not OPM-approved and so cannot be issued on government web sites. Previous level of response to survey has been low enough to consider ceasing this effort – discuss at next meeting. |
| 11: Re-post the post-event survey near March 11, 2012. Compile results and update report. | 3/12 | WCS co-Chairs, Pacific State/Terr. EM Reps. | Could not be done in time frame due to required OPM approval. |
| 12: Compose prototype messages considering Product Team’s suggestions and provide to WCS for review. | 5/12 | WCATWC - PTWC | Done – To be implemented 11/1/12 |
| 13: Chris to pose question to his focus groups: is it helpful to post tsunami travel time information when no tsunami is expected?, and report to co-chairs | 7/12 | Chris Gregg | Survey completed. Chris to report at meeting. |
| 14: Propose new offshore TIS procedures for west coast. . | 4/12 | WCATWC | Under review. |
| 15: Implement new PR/VI TIS procedures as suggested by Christa. | 2/12 | WCATWC | Done |
| 16: Review idea of scheduling conference calls on the hour. Proposal to be given to WCS. | 3/12 | WCATWC. | Done and enacted |