Action Items from the Third Meeting of the NTHMP Tsunami Warning Coordination Subcommittee

October 30, 2007 – Honolulu, Hawaii

May 27, 2008

| Action | Office | Status |
| --- | --- | --- |
| 1: Convene warning criteria review panel for WCATWC Pacific AOR. Forward report to all subcommittee members when complete. | WCATWC – reviewers | Done - Pacific region criteria review complete – to be published in Tsunami Hazards Journal |
| 2: Convene warning criteria review panel for WCATWC Atlantic AOR. | WCATWC – reviewers | Team to be assembled in June |
| 3: Review tsunami amplitude definitions in products and verify that PTWC/WCATWC use the same definitions. | WCATWC - PTWC | Done |
| 4: Provide examples of WCATWC products to subcommittee for review. These examples will show what the new advisory will look like, will remove ETAs from non-warning/watch areas, will move information below the segmented sections to above the segments, and will show what a message would look like if non-warning/watch areas are removed from the segmentation. Subcommittee members will be asked whether or not the non-warning/watch areas should be removed from the segmented part of the message. | WCATWC - Rulon | Done – new products to be implemented on 2/12/08 |
| 5: Examine how the NWS Comms. Integration Team can assist the roll-out of the new advisory product. Also see how the Team can assist with national media education on tsunami issues. | Maier | Chris will advise Comms Integration Team at next meeting (1/29) |
| 6: Provide California end-to-end test action plan to all subcommittee members and post this on the NTHMP web site. | Goltz | Done |
| 7: PTWC to work closely with Pacific insular territories on participating in Pac Wave ’08. | PTWC |  |
| 8: WCATWC to distribute all Pac Wave ’08 materials to subcommittee members. | WCATWC |  |
| 9: Examine if CISNDisplay can support an overlay of tsunami warning/watch areas. | Goltz |  |
| 10: Distribute prototype tsunami.gov real-time warning interface to group for review when developed by TWCs. | WCATWC | Tsunami.gov Con-ops development – PTWC/WCATWC team to meet in July for prototype development |
| 11: WCATWC to issue Information Statements to Pacific recipients when warnings are issued for Pacific or Indian Oceans. PTWC will examine if this procedure is needed for its customers. | WCATWC - PTWC | Done |
| 12: Establish method(s), procedure(s), and (if needed) product(s) for event conference call notifications. | Miller – Hinojosa - WCATWC | New AWIPS codes obtained to notify WFOs of conference call. An email/AWIPS message will be sent by WCATWC for Pacific calls. The Hurricane Hotline will be installed at the TWCs and will be used for east coast calls. |
| 13. Determine international involvement in Atlantic tsunami exercise. | Von Hillenbrandt | Not in 08/09. Possibly in 2010. |
| 14: Develop plan for an Atlantic exercise based on PAC Wave ’08 material for presentation at next subcommittee meeting. | WCATWC - Miller – Hinojosa - McCreery |  |
| 15: Expand this subcommittee’s Terms of Reference in light of the expanded composition of the NTHMP membership. | WCATWC – PTWC - Goltz | Done 12/2 |