Action Items from the Fourth Meeting of the NTHMP Warning Coordination Subcommittee

November 18, 2008 – Silver Spring, MD

Update – December 26, 2009

| Action | Date | Office | Status |
| --- | --- | --- | --- |
| 1: Complete Atlantic Warning Criteria Review and send to WCS members. | 6/09 | WCATWC – reviewers | Done – published in Tsunami Hazards Journal v28 #2, 2009. http://www.tsunamisociety.org/282WhitmoreEtAla.pdf |
| 2: Develop and implement procedures to use Hurricane Hotline during Atlantic w/w/a events. | 1/09 | WCATWC, PTWC, NWS ER, NWS SR | Done – implemented 1/30/09 |
| 3: Determine date for Atlantic exercise in 2009. | 12/08 | Whitmore, Ward, Williams, Miller, Hinojosa, von Hillebrandt | Done - April 2, 2009 at 1300UTC |
| 4: Create LANTEX09 handbook, distribute to WCS, and execute Atlantic exercise. | 1/09 | WCATWC – NWS ER – NWS SR | Final completed and distributed January 16, 2009. Exercise completed April 2, 2009. |
| 5: State partners distribute LANTEX09 handbook to counties and communities. NWS ER and SR tsunami program managers distribute to coastal WCMs. WCATWC coordinate with Storm Prediction Center in Canada. | 1/09 | NTHMP state/territory EM reps., Miller, Hinojosa, Whitmore | Telecon set for January 30, 2009 to discuss advertisement of exercise. Canada included in handbook distribution. Webinar conducted March 26, 2009. Press release issued in late-March. Exercise completed April 2, 2009 |
| 6: Obtain tsunami.gov requirements from WCS members. | 1/09 | WCATWC – WCS participants | Request sent to WCS 12/23/2008 – Responses included in web site development plan – 2/1/9. |
| 7: Develop implementation plan and date to implement new advisory definition and product in Hawaii. | 3/09 | PTWC | McCreery working with HCD on date to implement new advisory definition – March 1 for SCN, April 1 for implementation – 2010. |
| 8: Develop plan to convert usage of WCATWC break points to NWS public zones. | 10/09 | WCATWC | Plan developed and out for review. On next WCS meeting agenda for discussion. |
| 9: Change “No-repeat No- tsunami warning…” statement to new wording approved in meeting. | 1/09 | WCATWC | Done – implemented 12/08 |
| 10: Move w/w/a definitions below quake information. | 1/09 | WCATWC | Done – implemented 12/08 |
| 11: Add break points to “For information only…” section of w/w/a messages. | 6/09 | WCATWC | Done – implemented 6/29/09 |
| 12: Add scenario repository to WCATWC web site in non-public-linked location. Provide link to WCS. | 2/09 | WCATWC | Done - Scenario repository available at http://wcatwc.arh.noaa.gov/scenarios/index.php |
| 13: Propose changes to Terms of Reference to NTHMP CC. | 11/08 | Co-Chairs | Done and accepted by CC at 11/20/2008 CC meeting |
| 14: Develop plan for a Pacific exercise based on LANTEX09 material for presentation at next subcommittee meeting. | 10/09 | Whitmore – McCreery – Hendricks - Osiensky - Lorens | Decided on March 24, 2010 for both Atlantic and Pacific exercises. Atlantic handbook complete 12/10/9 and distributed, Pacific handbook complete and distributed in January. |
| 15: Develop WCS requirements for post-event survey. | 1/09 | Goltz – Diaz | Surveys completed and posted to NTHMP web site – one survey for the general public and one for emergency managers (6/09). |