2011 Meeting of the NTHMP Warning Coordination Sub. Action Items

February 1, 2011 – Portland, OR

Update – February 13, 2011

| Action | Date | Office | Status |
| --- | --- | --- | --- |
| 1: Hawaii CD rep. to check if Hawaii Chile Tsunami Response after action report can be shared | 3/11 | Hawaii CD |  |
| 2: Any other states who performed after action studies of the Chile Tsunami response to see if report can be shared with WCS through co-Chairs | 3/11 | State tsunami reps., WCS co-Chairs |  |
| 3: NOAA WCS co-Chairs to share Chile Tsunami Assessments with WCS as soon as released. | 3/11 | Paul Whitmore, Chip McCreery |  |
| 4: Issue NOAA Press Release in advance of CaribeWave11/PACIFEX11 exercises. | 3/10 | TPO |  |
| 5: Compile results from exercise feedback site into Atlantic exercise summary | 6/11 | WCATWC – PTWC - CTWP |  |
| 6: Compile results from exercise feedback site into Pacific exercise summary | 6/11 | WCATWC – PTWC |  |
| 7: Notify WCS co-Chairs when decision made for date/time of next international Pacific exercise. | 5/11 | ITIC |  |
| 8: Circulate proposed dates for 2012 national exercises to WCS for input | 2/11 | Paul Whitmore | March 28 proposed to co-Chairs |
| 9: Establish date for 2013 national exercises | 3/11 | WCS co-Chairs |  |
| 10: Finalize exercise handbooks for 2012 LANTEX exercise. | 12/11 | WCATWC – PTWC - CTWP |  |
| 11: Finalize exercise handbooks for 2012 PACIFEX exercise. | 12/11 | WCATWC – PTWC |  |
| 12: Query WCS members for input on tsunami.gov prototype when ready. | 5/11 | WCATWC |  |
| 13: Provide updates to WCS on development and initiation of Tsunami Local Statements | 7/11 | Jeff Lorens, WCS co-Chairs |  |
| 14: Complete 10-701 with updated domestic tsunami message format and issue SCN defining new forecast/observation format. | 5/11 | TPO - WCATWC – PTWC |  |
| 15: Provide updates to WCS on forecast inundation map and potential for current forecast distribution during warnings | 8/11 | Paul Whitmore and Chip McCreery |  |
| 16: State reps.query their communications staff about issuance of WCATWC Information Statements and scaled down verbiage of warnings and advisories on NAWAS. Whitmore to collect state input. | 3/11 | Paul Whitmore and NTHMP state EM tsunami reps. | 2/13 – Query sent to state reps. |
| 17: Dependent on response from above action, WCATWC adjust procedures for NAWAS announcements. | 5/11 | WCATWC |  |
| 18: Develop NTHMP template for ideal warning dissemination flow and post on web | 12/11 | WCS co-Chairs |  |