Action Items from the 2010 Meeting of the NTHMP Warning Coordination Subcommittee

January 26, 2010 – Pasadena, CA

Update – January 27, 2010

| Action | Date | Office | Status |
| --- | --- | --- | --- |
| 1: Notify WCS when NWS Samoa tsunami assessment is complete and where it is posted. | 4/10 | WCATWC - PTWC |  |
| 2: State EM NTHMP reps. and NWS regional Tsunami Program Managers distribute exercise handbooks to coastal county/local officials and coastal WCMs. | 2/10 | NTHMP State EM reps., NWS Tsunami Program Mgrs |  |
| 3: Coordinate LANTEX/PACFIEX with Atlantic Storm Prediction Center and BC PEP. | 2/10 | WCATWC |  |
| 3a. Coordinate with American Samoa regarding participation in exercise | 2/10 | PTWC |  |
| 3b. Coordinate with military prior to exercise | 2/10 | WCATWC/ARH |  |
| 4: Issue NOAA Press Release 1-2 weeks in advance of LANTEX/PACIFEX exercises. | 3/10 | TPO – WCATWC |  |
| 5: Determine date for 2011 national exercises. | 7/10 | WCS co-chairs, |  |
| 6: Develop exercise handbooks for 2011 LANTEX/PACIFEX exercises. | 12/10 | WCATWC – PTWC |  |
| 7: Issue SCN to remove marine zones from Pacific products and implement. | 3/10 | TPO–WR – AR – WCATWC |  |
| 8: Issue SCN to convert WCATWC breakpoints to NWS public zone boundaries and implement. | 6/10 | TPO – WRH – ARH – WCATWC |  |
| 9: Examine potential of refining PR/VI region by using public zone boundaries. | 6/10 | WCATWC – PRSN |  |
| 10: Dependent on Action 9, Issue SCN to convert PR/VI breakpoints to NWS public zone boundaries and implement. | 9/10 | TPO – SRH – WCATWC |  |
| 11: Adjust WCATWC procedures so that all M>=7.9 offshore events trigger multiple Info Stmts until it is verified no dangerous tsunami exists for AOR | 6/10 | WCATWC |  |
| 12: Adjust WCATWC criteria so that WCATWC Pacific TIS criteria mimic Atlantic TIS criteria | 6/10 | WCATWC |  |
| 13: Add content change lines for TWC supplemental w/w/a messages | 9/10 | WCATWC – PTWC |  |
| 14: Remove statements from Recommended Actions which are not Actions and place in appropriate place of message (reword “It is not known…”). | 4/10 | WCATWC |  |
| 15: Drop Juneau as WCATWC ETA site, add San Pedro, Replace Ketchikan with Craig | 3/10 | WCATWC |  |
| 16. Drop detailed PTWC actions from WCATWC products and list generic stmt on PTWC AOR. | 3/10 | WCATWC |  |
| 17: Consider possibility of changing survey to web-based survey after event | 8/10 | Goltz, Diaz, Whitmore |  |
| 18: Ensure appropriate baseline warning reception/dissemination data is captured and collated in MES surveys | 12/10 | Co-Chairs |  |
| 19. Recommend to CC that NTHMP develop response plan for major events like Samoa. | 1/10 | Co-Chairs |  |